## Sheet1
Date | Duration | Task | Status To Kirk
2014-01-17 | 3 | Create Ribbon and Add functionality to Add/Remove Slides
2014-01-20 | 3 | Create the UI functionality for "Create Task"
2014-01-21 | 3 | Integrate UI with API to send and retrieve Data. | Email intermediate Status.
2014-01-22 | 3 | Test "Create Task" and implement any changes necessary.
2014-01-23 | 3 | Give Demo to Kirk and Implement any changes requested. | Demo of "Create Task" Functionality
2014-01-24 | 3 | Create the UI functionality for "Asset Library"
2014-01-27 | 4 | Integrate UI with API to send and retrieve data. | Email Intermediate Status
2014-01-28 | 4 | Test "Asset Library" and implement any changes necessary.
2014-01-29 | 4 | Give Demo to Kirk and implement any changes requested. | "Demo of Asset Library" Functionality
2014-01-30 | 4 | Implement final changes if necessary and Handoff the project
Total | 34